## Timeline
SAMPLE EVENT TIMELINE FOR NOV 1 EVENT | Month of… | [6 empty] | Week of
Key Task List | February | March | April | May | June | July | Aug | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | Comments
Leadership Kickoff | x
Establish Event Budget | x
Commitee Recruitment |  | x
Set up Software |  | x
Select T-shirt color if doing shirts |  | x
Select date and location if in person event
Create Invite |  |  | x
Create Sponsor Flyer |  |  | x
Committee Kickoff |  |  |  | x
Approach Sponsors |  |  |  | x | x | x | x | bar: 2022-08-29 to 2022-09-19
Send STD |  |  |  |  | x
Recruit Team Captains |  |  |  |  | x | x | x | bar: 2022-08-29 to 2022-10-10
Send Invitation | [6 empty] | x
Ticket site Live | bar: 2022-08-29
Team Captain Kick-Off Mtg | bar: 2022-09-05
Recruit participants | [6 empty] | x | bar: 2022-08-29 to 2022-10-31
Finalize in person event details | [6 empty] | x | bar: 2022-08-29 to 2022-10-31
Finalize Sponsors | bar: 2022-10-10
Order Shirts (1st order) | [18 empty] | to gaurantee by event date | bar: 2022-10-10
Thank you email / Sponsor thank yous | bar: 2022-11-07
Order Shirts (2nd order) | [18 empty] | post event | bar: 2022-11-07
Commmittee debrief | bar: 2022-11-07
Post event financials | bar: 2022-11-07